## V1
Project Development and Completion Tracker
Porject ID:116
Project Start Date: 15-05-2024 Project End Date:
Porject Descreption: Plant's Leaf Image Disease Detector
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | Om Talekar |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
| Shruti Thorat |  |  |  |  | Frond End
| Karthik Devkar |  |  |  |  | Team Lead
| Sujal Hande |  |  |  |  | Front/Back End
Epic: | Plant Leaf Disease Detection System Development
Story 1: | As a plant owner or gardener,I want to upload an image of my plant leaf so that I can quickly detect if there is any disease affecting my plant and take appropriate actions.
Story 2: | As a non-expert plant owner,I want to receive a simple, understandable disease diagnosis along with the severity of the disease so that I can act accordingly, whether it’s applying treatment or seeking professional help.
Story 3: | As a concerned plant owner,I want to receive clear treatment suggestions and preventive measures tailored to the specific disease detected, so I can care for my plant and prevent future issues.
Task1: | Define objectives, user needs, and features
Task2: | Gather images of healthy and diseased plant leaves
Task3: | Research and select model architecture
Task4: | Develop a user-friendly form for uploading leaf images.
Task5: | Develop buttons, sliders, and display areas to show disease results and treatment suggestions.
Acceptance Criteria:
1 | Image Upload & Disease Detection: Users can upload plant leaf images in supported formats, receive an accurate disease diagnosis within 10 seconds, and view treatment suggestions if disease is detected.
2 | login layout suports gmail/ contact number/ Aadhar number (future scope) credetials with input validations.
3 | Security & Performance: User data is stored securely, transmitted over HTTPS, and the website maintains high performance, loading within 3 seconds and handling up to 100 users.
4 | User Feedback & Learning Resources: Users can provide feedback on detection results, and a section with plant care articles is updated regularly.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Data Collection and Preprocessing considering various lighting and environmental conditions. | Collect and organize diverse plant leaf datasets | Complete | Shruti,Kartik | 2024-07-03 | 2024-11-21 | 2024-07-06 | 2024-07-12 | 100% | Not Started | Medium
|  | Label images by disease type, plant type | Complete | Sujal,Om | 2024-07-18 | 2024-11-21 | 2024-07-06 | 2024-08-02 | 100%
| Machine Learning Model Development | Set up the model development environment | Complete | Sujal,Kartik | 2024-08-13 | 2024-11-21 | 2024-07-06 | 2024-08-28 | 100% | In Progress | Low
|  | Create a baseline model structure and load sample data for testing. | Complete | Kartik,Om | 2024-09-03 | 2024-11-21 | 2024-07-06 | 2024-09-12 | 100%
| Project Management and Documentation | Set up project timeline, goals, and deliverables. | Complete | Sujal | 2024-09-18 | 2024-11-21 | 2024-07-06 | 2024-09-23 | 100% | Complete | High
|  | Document initial setup and decisions, and gather feedback for adjustments. | Complete | Om | 2024-09-20 | 2024-11-21 | 2024-07-06 | 2024-09-27 | 100%
Sprint 1 | Data Collection and Preprocessing | Review and improve preprocessing steps based on model performance feedback. | Complete | Shruti | 2024-10-01 | 2024-11-21 | 2024-07-06 | 2024-10-09 | 100% | On Hold
| Mobile or Web Application Development | Develop core features of the user-friendly platfrom (image upload, result display). | Complete | All Team Members | 2024-10-14 | 2024-11-21 | 2024-07-06 | 2024-10-22 | 100% | Overdue
Sprint 2 | Data Collection and Preprocessing | Prepare documentation on final data preparation steps and data challenges. | Complete | Shruti,Om | 2024-10-24 | 2024-11-21 | 2024-07-06 | 2024-10-29 | 100%
| Project Management and Documentation | Conduct final project review and Compile all documentation | Complete | All Team Members | 2024-11-06 | 2024-11-21 | 2024-07-06 | 2024-11-21 | 100%

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%